## Project Overview
AGILE PROJECT OVERVIEW
Project | Intelligent Bug Diagnosis Platform with Fix Recommendation Assistance
Methodology | Agile Scrum
Project Goal | Automatically analyze software bugs, identify root causes, detect duplicates, retrieve similar historical bugs, and recommend fixes.
Technology | Python, Flask, SQLite, FAISS, Sentence Transformers, RAG, Multi-Agent AI, HTML/CSS/JavaScript
Milestone 1 | Foundation: project setup, Flask API, SQLite database, bug submission and basic workflow.
Milestone 2 | Intelligent Analysis: RAG knowledge base, FAISS similarity search, triage/log/root-cause agents, duplicate detection.
Milestone 3 | Recommendation & Reporting: remediation/fix recommendations, structured findings, dashboard, analytics and exports.
Milestone 4 | Automation & Quality: Auto-Watch folder ingestion, watcher APIs, event tracking, Agile documentation, testing and deployment readiness.
Definition of Done | Feature implemented, integrated with backend/frontend, tested, documented, and verified through API or end-to-end testing.

## Product Backlog
ID | Item | Details
PB1 | Bug Submission | Users submit bug reports
PB2 | Knowledge Base | Store historical bugs
PB3 | Similarity Search | FAISS retrieval
PB4 | Duplicate Detection | Detect similar bugs
PB5 | Dashboard | Analytics
PB6 | Bug Triage | Classify incoming bugs by severity, priority, category and component.
PB7 | Log Analysis | Extract useful error messages, exceptions, stack traces and patterns from logs.
PB8 | Root Cause Analysis | Identify the probable technical root cause using the multi-agent pipeline.
PB9 | Remediation Recommendation | Generate practical fix recommendations for identified root causes.
PB10 | Auto-Watch | Monitor the configured logs folder and automatically ingest new .log/.txt files.
PB11 | Watch Event Tracking | Store detected, processed and failed file events in SQLite.
PB12 | Analytics | Show total defects, severity/status/category statistics and project trends.
PB13 | Reports & Export | Provide CSV/PDF bug and analytics reports.
PB14 | Knowledge Promotion | Promote resolved and verified bugs into the RAG knowledge base.
PB15 | Testing | Validate APIs, duplicate detection, watcher behavior, analytics, reports and knowledge retrieval.
PB16 | Documentation | Maintain technical, Agile, testing and project documentation.

## Sprint Backlog
ID | Item | Details | Status
S1 | Milestone 1 - Project Foundation | Setup Flask application, configuration, SQLite database, models and basic API. | Completed
S2 | Milestone 1 - Bug Submission | Implement bug submission, validation, storage and initial bug status workflow. | Completed
S3 | Milestone 1 - Basic UI | Create bug submission and bug listing/dashboard foundation. | Completed
S4 | Milestone 2 - RAG Knowledge Base | Create knowledge base and integrate Sentence Transformers with FAISS. | Completed
S5 | Milestone 2 - Similarity Search | Retrieve similar historical bugs using semantic similarity. | Completed
S6 | Milestone 2 - Multi-Agent Analysis | Integrate triage, log analysis and root-cause analysis agents. | Completed
S7 | Milestone 2 - Duplicate Detection | Detect duplicate or highly similar bug reports. | Completed
S8 | Milestone 3 - Remediation | Generate fix/remediation recommendations from analysis results. | Completed
S9 | Milestone 3 - Structured Findings | Return consistent findings for severity, root cause, evidence and recommendation. | Completed
S10 | Milestone 3 - Dashboard & Analytics | Implement analytics, defect statistics and visual dashboard information. | Completed
S11 | Milestone 3 - Reports | Implement CSV/PDF export functionality for bug and analytics reports. | Completed
S12 | Milestone 4 - Auto-Watch | Monitor logs folder and automatically process new .log/.txt files. | Completed
S13 | Milestone 4 - Watch Events | Track detected, processed, skipped and failed files. | Completed
S14 | Milestone 4 - API Integration | Expose watcher status, scan, start and stop APIs. | Completed
S15 | Milestone 4 - Testing | Run unit/end-to-end tests and fix compatibility issues. | In Progress
S16 | Milestone 4 - Documentation & Deployment | Finalize Agile documents, README, license and deployment readiness. | In Progress

## Stand-up Meeting
Day | Milestone | Task | Work Done | Status
Day 1 | Milestone 1 | Project setup | Configured Python/Flask environment and project structure. | Completed
Day 2 | Milestone 1 | Database & APIs | Implemented SQLite database, bug model and basic REST endpoints. | Completed
Day 3 | Milestone 1 | Bug workflow | Implemented bug submission, status handling and initial dashboard. | Completed
Day 4 | Milestone 2 | Knowledge base | Integrated RAG pipeline, embeddings and FAISS index. | Completed
Day 5 | Milestone 2 | Similarity search | Implemented semantic retrieval of similar historical bugs. | Completed
Day 6 | Milestone 2 | AI analysis | Integrated triage, log analysis and root-cause analysis agents. | Completed
Day 7 | Milestone 2 | Duplicate detection | Connected similarity results to duplicate detection workflow. | Completed
Day 8 | Milestone 3 | Remediation | Added fix recommendation and remediation analysis. | Completed
Day 9 | Milestone 3 | Structured findings | Standardized analysis output for dashboard and reports. | Completed
Day 10 | Milestone 3 | Analytics | Added defect statistics, status/severity summaries and dashboard data. | Completed
Day 11 | Milestone 3 | Reports | Implemented bug/report export functionality. | Completed
Day 12 | Milestone 4 | Auto-Watch | Implemented folder scanning and automatic .log/.txt ingestion. | Completed
Day 13 | Milestone 4 | Watch events | Added database event tracking and rescan/skip behavior. | Completed
Day 14 | Milestone 4 | Watcher APIs | Added status, scan, start and stop endpoints. | Completed
Day 15 | Milestone 4 | Testing | Executed end-to-end tests and identified remaining integration issues. | In Progress
Day 16 | Milestone 4 | Finalization | Preparing final documentation, GitHub repository and deployment/demo. | In Progress

## Retrospection
Sprint/Milestone | What Went Well | What Could Improve | Action Taken / Next Step
Milestone 1 | Flask and SQLite foundation was established and core bug workflow became functional. | Initial schema and API contracts needed better planning. | Standardize database helpers and API response structures.
Milestone 2 | RAG, FAISS similarity search and multi-agent analysis were successfully integrated. | Knowledge-base seeding and retrieval needed stronger validation. | Add deterministic test data and verify index size/retrieval after promotion.
Milestone 3 | Remediation, structured findings, dashboard and reporting features were integrated. | Export formats and analytics field names required stricter test alignment. | Use fixed response contracts and add regression tests for CSV/PDF exports.
Milestone 4 | Auto-Watch, scan APIs and watch-event persistence were implemented. | Watcher behavior and event history needed more end-to-end validation. | Verify processed/skipped events, database persistence and watcher status in tests.
Team Process | Agile backlog and milestone-based development kept tasks organized. | Some integration work was completed late in the cycle. | Review API contracts earlier and run the full test suite after every milestone.
Final Goal | The platform now covers automated bug analysis from ingestion to recommendations. | Final deployment and documentation still need verification. | Complete remaining tests, finalize Agile documentation, license, README and deployment.